## Machine Work Orders
Applied filters: ITEMNUMBER is not 02002107 SC2 is Electmech, Machine, or Hydraulic SC1 is Automated, FoldingEnd, HDT, Met-Impact, MFI, Plas-Impac, Retrofit, SL-Series, Torsion, or Horizontal Status is not Completed or ReportedFinished SALESORDERPOOLID does not contain 'Consign'
Resource | ENGINEERINGNOTES | SALESORDERNUMBER | MCRORDERSTOPPED | SALESORDERNAME | ITEMNUMBER | Earliest DELIVERYDATE | Start Date | SC3
365072/Paint/Assy03/ Started/1 |  | 596324 | 0 | CORINCA CORP IND CENTROAMERICANA | 09010600 | 2026-06-19 | 2026-06-01 | 2000SL
365434/R&D/R&DEngUS/ Started/1 | Paul Feudo | 594858 | 1 | ELLWOOD Materials Technologies Lab Co | 04002600 | 2026-09-18 | 2026-06-02 | SL-ST
364732/W/H-End// Started/1 |  | 595518 | 0 | Mid-West Mfg. LLC | 09010630 | 2026-07-30 | 2026-06-08 | 2000SL
366649/REP_Assy/Assy03/ Started/1 |  | 595872 | 0 | Nucor-Yamato Steel Co. | Fee-999-MetImp | 2026-09-30 | 2026-06-15 | Misc
366203/Assembly/Assy04/ Started/1 |  | 700524 | 0 | Nucor Towers and Structures | 12004053 | 2026-08-05 | 2026-06-17 | IT406
365659/Calib/Cal_GEN/ Started/1 |  | 599155 | 0 | Avient Corporation | 02005261 | 2026-07-29 | 2026-06-22 | HDVT3
364461/Assembly/Assy07/ Started/1 |  | 595132 | 0 | Taylor Forge | 09002600 | 2026-08-28 | 2026-06-26 | 600SL
365274/Calib/Assy10/ Started/1 | Marcus Mihulec | 596256 | 0 | GERDAU AMERISTEEL WHITBY | 09010630 | 2026-08-27 | 2026-07-06 | 2000SL
365568/Calib/Cal_GEN/ Started/1 |  | 598839 | 0 | Middle Tennessee State University | 10011130 | 2026-08-25 | 2026-07-07 | Torsion
366208/W/H-End// Started/1 |  | 700527 | 0 | Nucor Towers and Structures | 09001300 | 2026-08-13 | 2026-07-09 | 300SL
365341/Assembly/Assy10/ Started/1 |  | 596498 | 0 | ACUREN | 09009410 | 2026-09-04 | 2026-07-13 | 1000SL
365450/Assembly/Assy09/ Started/1 |  | 596952 | 0 | Tinius Olsen Testing Machine Shanghai Co Ltd | 09002620 | 2026-08-20 | 2026-07-13 | 600SL
365451/W/H-Hold/Assy04/ Started/1 |  | 596952 | 0 | Tinius Olsen Testing Machine Shanghai Co Ltd | 12004051 | 2026-08-28 | 2026-07-16 | IT406
365449/Assembly/Assy06/ Started/1 |  | 596798 | 0 | PowerCept Middle East Mechanical & Engineering Equipment Trading LLC | 09010610 | 2026-09-21 | 2026-07-27 | 2000SL
365267/Assembly/Assy07/ Started/1 |  | 596655 | 0 | KTH Parts Industries Inc. | 09002600 | 2026-09-17 | 2026-07-31 | 600SL
364885/Assembly/Assy09/ Started/1 |  | 593042 | 0 | DFAS ROCK ISLAND - HQ0303 | 09001330 | 2026-09-16 | 2026-08-05 | 300SL
366129/Assembly/Assy07/ Started/1 |  | 700471 | 0 | Element | 09001300 | 2026-09-02 | 2026-08-06 | 300SL
366476/W/H-Hold/GenAssy/ Started/1 |  | 701140 | 0 | Jubail Energy Services Company | 09010610 | 2026-10-02 | 2026-08-10 | 2000SL
366477/W/H-Start/GenAssy/ Started/1 |  | 701140 | 0 | Jubail Energy Services Company | 09002610 | 2026-10-02 | 2026-08-14 | 600SL
366207/W/H-Start/GenAssy/ Released/1 |  | 700526 | 0 | Nucor Towers and Structures | 12004053 | 2026-09-29 | 2026-08-18 | IT406
364886/W/H-Hold/GenAssy/ Started/1 |  | 593042 | 0 | DFAS ROCK ISLAND - HQ0303 | 09001330 | 2026-09-30 | 2026-08-19 | 300SL
366947/W/H-Start/GenElec/ Started/1 |  | 702749 | 0 | Hoeganaes Corporation | 03072058 | 2026-09-03 | 2026-08-19 | NO-CNSL
367128/Calib/Cal_GEN/ Started/1 |  | 703702 | 0 | Oldcastle Precast | 02002310 | 2026-08-27 | 2026-08-20 | MP1200MWLD
365365/W/H-Start/GenAssy/ Released/1 |  | 596759 | 0 | Pacific Steel Group | 09010630 | 2026-10-16 | 2026-08-24 | 2000SL
366249/W/H-Start/GenAssy/ Released/1 |  | 599702 | 0 | City of Tucson | 03072062 | 2026-09-14 | 2026-08-25 | CNSL-HYD
367034/W/H-Start/Cal_GEN/ Released/1 |  | 703019 | 0 | HI SHEAR CORPORATION | 03072069 | 2026-09-03 | 2026-08-26 | NO-CNSL
366113/W/H-Start/GenAssy/ Released/1 |  | 700241 | 0 | Jennmar Corporation | 09002600 | 2026-10-16 | 2026-08-28 | 600SL
366972/Electrical/Elec01/ Started/1 | Catherine Stencler | 702747 | 0 | Arrowhead Products | 03072073 | 2026-09-08 | 2026-08-28 | NO-CNSL
367035/W/H-Start/GenElec/ Scheduled/1 |  | 703211 | 0 | Feralloy Corporation | 03072066 | 2026-09-10 | 2026-08-28 | NO-CNSL
366541/W/H-Start/GenAssy/ Released/1 |  | 701595 | 0 | CEMEX | 09001320 | 2026-10-14 | 2026-09-01 | 300SL
366771/W/H-Start/GenAssy/ Released/1 |  | 702457 | 0 | ARKANSAS STATE UNIVERSITY | 03072059 | 2026-09-17 | 2026-09-07 | CNSL-NOHYD
365908/W/H-Start/GenAssy/ Released/1 |  | 596794 | 0 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09009410 | 2026-11-02 | 2026-09-08 | 1000SL
366479/W/H-Start/GenAssy/ Released/1 |  | 701140 | 0 | Jubail Energy Services Company | 12004062 | 2026-10-30 | 2026-09-10 | IT542
367003/W/H-Start/GenAssy/ Released/1 |  | 702848 | 0 | Howmet Fastening Systems | 09002600 | 2026-10-29 | 2026-09-11 | 600SL
367125/W/H-Start/GenElec/ Released/1 |  | 703546 | 0 | Pacific Woodtech | 03072068 | 2026-09-23 | 2026-09-11 | NO-CNSL
365312/W/H-Start/Cal_GEN/ Released/1 |  | 596734 | 0 | TO Korea Co Ltd | 02005151 | 2026-10-07 | 2026-09-16 | HDVT6
365843/W/H-Start/GenAssy/ Released/1 |  | 596793 | 0 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09001310 | 2026-10-27 | 2026-09-16 | 300SL
365903/W/H-Start/GenAssy/ Released/1 |  | 596725 | 0 | ACUREN | 09009410 | 2026-11-13 | 2026-09-21 | 1000SL
367118/W/H-Start/Cal_GEN/ Released/1 |  | 702930 | 0 | AVIBANK MFG INC | 03072069 | 2026-10-02 | 2026-09-24 | NO-CNSL
367119/W/H-Start/Cal_GEN/ Released/1 |  | 702930 | 0 | AVIBANK MFG INC | 03072069 | 2026-10-02 | 2026-09-24 | NO-CNSL
366112/W/H-Start/GenAssy/ Released/1 |  | 700233 | 0 | Flash Steelworks | 09002610 | 2026-11-12 | 2026-09-25 | 600SL
367130/W/H-Start/GenElec/ Released/1 |  | 703738 | 0 | Gulfstream Aerospace | 03072060 | 2026-10-07 | 2026-09-25 | NO-CNSL
365846/W/H-Start/GenAssy/ Released/1 |  | 596793 | 0 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09001310 | 2026-11-10 | 2026-09-30 | 300SL
366045/W/H-Start/GenAssy/ Released/1 |  | 599466 | 0 | Jennmar Corporation of VA, Inc. | 09010600 | 2026-12-01 | 2026-10-05 | 2000SL
366865/W/H-Start/GenAssy/ Released/1 |  | 702746 | 0 | Merit Steel Company | 09002610 | 2026-11-30 | 2026-10-09 | 600SL
366212/W/H-Start/GenElec/ Released/1 |  | 700529 | 0 | Nucor Steel Company | 09001300 | 2026-11-25 | 2026-10-14 | 300SL
367005/W/H-Start/GenElec/ Released/1 |  | 702848 | 0 | Howmet Fastening Systems | 09001300 | 2026-12-01 | 2026-10-16 | 300SL
366802/W/H-Start/GenAssy/ Released/1 |  | 702663 | 0 | Phoenix Tube Co. | 09009410 | 2026-12-15 | 2026-10-19 | 1000SL
365168/W/H-Start/W/H-Start/ Released/1 |  | 596507 | 0 | Element | 09001300 | 2026-12-09 | 2026-10-28 | 300SL
365854/W/H-Start/GenAssy/ Released/1 |  | 596795 | 0 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 12004053 | 2026-12-10 | 2026-10-30 | IT406
365855/W/H-Start/GenAssy/ Released/1 |  | 596795 | 0 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 12004053 | 2026-12-14 | 2026-10-30 | IT406
366656/W/H-Start/GenAssy/ Released/1 |  | 702215 | 0 | Liberty Lift Solutions, LLC | 09009410 | 2027-01-07 | 2026-11-02 | 1000SL
366898/W/H-Start/GenElec/ Released/1 |  | 702878 | 0 | Conmet de México, S. A. de C. V. | 09001300 | 2026-12-23 | 2026-11-11 | 300SL
366211/W/H-Start/GenAssy/ Released/1 |  | 700528 | 0 | Nucor Steel Company | 12004053 | 2027-01-15 | 2026-11-24 | IT406
366715/W/H-Start/GenAssy/ Released/1 |  | 701859 | 0 | North Star BlueScope Steel | 12004062 | 2027-02-12 | 2027-01-06 | IT542
366864/W/H-Start/GenAssy/ Released/1 |  | 702742 | 0 | The QUIKRETE Companies, LLC | 12004053 | 2027-03-08 | 2027-01-28 | IT406
366716/W/H-Start/Cal_GEN/ Released/1 |  | 701859 | 0 | North Star BlueScope Steel | 12002311 | 2027-02-05 | 2027-01-29 | 799
367043/W/H-Start/GenAssy/ Released/1 |  | 703350 | 0 | Naval Surface Warfare Center | 12004062 | 2027-04-23 | 2027-03-17 | IT542
367060/W/H-Start/GenAssy/ Released/1 |  | 703246 | 1 | McAuliffe’s Industrial | 12004062 | 2027-06-10 | 2027-05-03 | IT542

## Related order details
Ship Status | Weeks Late | S/O #(salesordernumber) | Name | Item Number | Description | Qty | Config | Ship date | Ref # | Status(ProductionOrderStatus) | Lead Eng. | Open (Wks) | Ship Time(Wks) | SC1 | SC3 | S/O Created on
| 0 | 703879 | Chevron Phillips Chemical Co. LP | 02002321 | MP1200 MWLD Std Furnace & Die Release, Purge & Clean | 2 | 02002321-110V | 2026-09-23 |  |  |  | 0.080529 | 5.0805 | MFI | MP1200ETO | 2026-08-18 10:28
| 0 | 703843 | Tinius Olsen Limited | 12002311 | Model 799D Notch Verification Device (Digital), High Resolution .00005"/.001mm | 1 |  | 2026-09-08 |  |  |  | 0.26526 | 3.1224 | Plas-Impac | 799 | 2026-08-17 03:26
| 0 | 703783 | Qualis Engineered Plastics | 02002300 | MP1200 Melt Indexer, Std Furnace, w/Die Release | 1 | 02002300-110V | 2026-08-31 |  |  |  | 0.78966 | 2.5039 | MFI | MP1200MAN | 2026-08-13 11:20
| 0 | 703781 | Qualis Engineered Plastics | 12002311 | Model 799D Notch Verification Device (Digital), High Resolution .00005"/.001mm | 1 |  | 2026-09-23 |  |  |  | 0.79294 | 5.7929 | Plas-Impac | 799 | 2026-08-13 10:47
| 0 | 703781 | Qualis Engineered Plastics | 12003023 | IT504 Plastic Impact Tester for Izod | 1 | 12003023-110V | 2026-09-23 |  |  |  | 0.79294 | 5.7929 | Plas-Impac | IT504 | 2026-08-13 10:47
| 0 | 703738 | Gulfstream Aerospace | 03072060 | Retrofit, Super "L" Digital/Servo with 290/398 496 Console to VMC | 1 | 03072060-Normal | 2026-10-07 | 367130 | Released |  | 0.96014 | 7.9601 | Retrofit | NO-CNSL | 2026-08-12 06:42
| 0 | 703716 | PT Prolabmas Murni Swadaya | 02005261 | Model HDVT3, Heat Deflection | 1 | 02005261-3Station | 2026-10-29 |  |  |  | 1.0766 | 11.2194 | HDT | HDVT3 | 2026-08-11 11:08
| 0 | 703702 | Oldcastle Precast | 02002310 | MP1200 MWLD, Std Furnace, w/Die Release | 1 | 02002310-110V | 2026-08-27 | 367128 | Started |  | 1.1033 | 2.2462 | MFI | MP1200MWLD | 2026-08-11 06:38
| 0 | 703664 | Dubose National Energy Services Inc. | 03072069 | Retrofit, Super "L" 602 Servo to VMC | 1 | 03072069-602-VMC-PS | 2026-08-28 |  |  |  | 1.2468 | 2.5326 | Retrofit | NO-CNSL | 2026-08-10 06:32
| 0 | 703546 | Pacific Woodtech | 03072068 | Retrofit, Super "L" Digital/Servo with 602 & 398/496 Console to VMC | 1 | 03072068-Normal-W | 2026-09-23 | 367125 | Released |  | 1.9564 | 6.9564 | Retrofit | NO-CNSL | 2026-08-05 07:19
| 0 | 703350 | Naval Surface Warfare Center | 12004062 | Model IT542 Motorized Pendulum Impact Tester with Dig Disp, Encl and Pne Release | 1 | 12004062-160 | 2027-04-23 | 367043 | Released |  | 3.0879 | 38.3736 | Met-Impact | IT542 | 2026-07-28 09:14
| 0 | 703246 | McAuliffe’s Industrial | 12004062 | Model IT542 Motorized Pendulum Impact Tester with Dig Disp, Encl and Pne Release | 1 | 12004062-160 | 2027-06-10 | 367060 | Released |  | 3.8072 | 45.95 | Met-Impact | IT542 | 2026-07-23 08:24
| 0 | 703211 | Feralloy Corporation | 03072066 | Retrofit, Super "L" 602 Manual Console to VMC | 1 | 03072066-SS | 2026-09-10 | 367035 | Scheduled |  | 3.9629 | 7.1058 | Retrofit | NO-CNSL | 2026-07-22 06:14
| 0 | 703092 | Granges Americas, Inc. | 08005110 | MMHT-5000 Horizontal Testing Machine, VMC Control, Custom to Order | 1 | 08005110-703092 | 2027-05-31 |  |  |  | 4.6767 | 45.391 | Horizontal | MMHT | 2026-07-17 06:19
| 0 | 703019 | HI SHEAR CORPORATION | 03072069 | Retrofit, Super "L" 602 Servo to VMC | 1 | 03072069-602-VMC | 2026-09-03 | 367034 | Released |  | 5.0951 | 7.2379 | Retrofit | NO-CNSL | 2026-07-14 08:02
| 0 | 702930 | AVIBANK MFG INC | 03072069 | Retrofit, Super "L" 602 Servo to VMC for 120K s/n 319713 | 1 | 03072069-602-VMC-PS | 2026-10-02 | 367118 | Released |  | 5.6705 | 11.9562 | Retrofit | NO-CNSL | 2026-07-10 07:22
| 0 | 702930 | AVIBANK MFG INC | 03072069 | Retrofit, Super "L" 602 Servo to VMC for 200K s/n 200308 | 1 | 03072069-602-VMC-PS | 2026-10-02 | 367119 | Released |  | 5.6705 | 11.9562 | Retrofit | NO-CNSL | 2026-07-10 07:22
| 0 | 702878 | Conmet de México, S. A. de C. V. | 09001300 | Model 300SL, Rack & Pinion | 1 | 09001300-CL0-LV | 2026-12-23 | 366898 | Released |  | 5.8038 | 23.8038 | SL-Series | 300SL | 2026-07-09 08:57
| 0 | 702848 | Howmet Fastening Systems | 09001300 | Model 300SL, Rack & Pinion | 1 | 09001300-CL0-HV | 2026-12-01 | 367005 | Released |  | 5.9453 | 20.8025 | SL-Series | 300SL | 2026-07-08 09:11
| 0 | 702848 | Howmet Fastening Systems | 09002600 | Model 600SL, Rack & Pinion | 1 | 09002600-CL1-HV | 2026-12-01 | 367003 | Released |  | 5.9453 | 20.8025 | SL-Series | 600SL | 2026-07-08 09:11
| 0 | 702749 | Hoeganaes Corporation | 03072058 | Retrofit, Super "L" with Dial Housing to VMC SN 133635 | 1 | 03072058-MM-120 | 2026-09-03 | 366947 | Started |  | 6.6578 | 8.8007 | Retrofit | NO-CNSL | 2026-07-03 09:29
| 0 | 702747 | Arrowhead Products | 03072073 | Retrofit, ETM 602 Manual Control to VMC - 120K ETM #81175 | 1 | 03072073-TorqueBar | 2026-09-08 | 366972 | Started | Catherine Stencler | 6.6628 | 9.5199 | Retrofit | NO-CNSL | 2026-07-03 08:39
| 0 | 702746 | Merit Steel Company | 09002610 | Model 600SL, Hydraulic Lever | 1 | 09002610-CL1-LV | 2026-10-30 | 366865 | Released |  | 6.6628 | 16.9485 | SL-Series | 600SL | 2026-07-03 08:39
| 0 | 702742 | The QUIKRETE Companies, LLC | 12004053 | Model IT406 Motorized Pendulum Impact Tester with Digital Display & Enclosure | 1 | 12004053-160 | 2027-03-12 | 366864 | Released |  | 6.6717 | 35.9574 | Met-Impact | IT406 | 2026-07-03 07:09
| 0 | 702663 | Phoenix Tube Co. | 09009410 | Model 1000SL, Hydraulic Lever | 1 | 09009410-CL0-LV | 2027-01-25 | 366802 | Released |  | 7.0641 | 29.7784 | SL-Series | 1000SL | 2026-06-30 13:14
| 0 | 702457 | ARKANSAS STATE UNIVERSITY | 03072059 | Retrofit, Super "L" Digital/Servo with LoCap Console (3 Piece) to VMC | 1 | 03072059-STD-3P | 2026-09-17 | 366771 | Released |  | 8.221 | 12.3638 | Retrofit | CNSL-NOHYD | 2026-06-22 10:52
| 0 | 702215 | Liberty Lift Solutions, LLC | 09009410 | Model 1000SL, Hydraulic Lever | 1 | 09009410-CL0-HV | 2027-02-16 | 366656 | Released |  | 9.7961 | 35.6532 | SL-Series | 1000SL | 2026-06-11 10:16
| 0 | 701859 | North Star BlueScope Steel | 12002311 | Model 799D Notch Verification Device (Digital), High Resolution .00005"/.001mm | 1 |  | 2027-02-12 | 366716 | Released |  | 11.8139 | 37.0996 | Plas-Impac | 799 | 2026-05-28 07:16
| 0 | 701859 | North Star BlueScope Steel | 12004062 | Model IT542 Motorized Pendulum Impact Tester with Dig Disp, Encl and Pne Release | 1 | 12004062-160 | 2027-02-12 | 366715 | Released |  | 11.8139 | 37.0996 | Met-Impact | IT542 | 2026-05-28 07:16
| 0 | 701595 | CEMEX | 09001320 | Model 300SL, Compression only | 1 | 09001320-S-HV | 2026-11-09 | 366541 | Released |  | 13.2458 | 24.9601 | SL-Series | 300SL | 2026-05-18 06:43
| 0 | 701140 | Jubail Energy Services Company | 09002610 | Model 600SL, Hydraulic Lever 400/60/3 | 1 | 09002610-CLO-HV | 2026-11-30 | 366477 | Started |  | 15.9554 | 30.6697 | SL-Series | 600SL | 2026-04-29 07:29
| 0 | 701140 | Jubail Energy Services Company | 09010610 | Model 2000SL, Hydraulic Lever 400/60/3 | 1 | 09010610-CL0-HV | 2026-11-30 | 366476 | Started |  | 15.9554 | 30.6697 | SL-Series | 2000SL | 2026-04-29 07:29
| 0 | 701140 | Jubail Energy Services Company | 12004062 | Model IT542 Motorized Pendulum Impact Tester with Dig Disp, Encl and Pne Release | 1 | 12004062-260 | 2026-11-30 | 366479 | Released |  | 15.9554 | 30.6697 | Met-Impact | IT542 | 2026-04-29 07:29
Late | 11.1429 | 700640 | DENSO International America, Inc. | 02002410 | MP1500 Melt Indexer w/Clean | 1 | STD | 2026-08-17 |  |  |  | 18.8164 | 18.5307 | MFI | MP1500 | 2026-04-09 06:51
| 0 | 700529 | Nucor Steel Company | 09001300 | Model 300SL, Rack & Pinion | 1 | 09001300-CL0-HV | 2027-01-15 | 366212 | Released |  | 19.4664 | 40.7521 | SL-Series | 300SL | 2026-04-04 17:38
| 0 | 700528 | Nucor Steel Company | 12004053 | Model IT406 Motorized Pendulum Impact Tester with Digital Display and Enclosure | 1 | 12004053-160 | 2027-01-15 | 366211 | Released |  | 19.4665 | 40.7522 | Met-Impact | IT406 | 2026-04-04 17:38
| 0 | 700527 | Nucor Towers and Structures | 09001300 | Model 300SL, Rack & Pinion | 1 | 09001300-CL0-HV | 2026-10-01 | 366208 | Started |  | 19.4665 | 25.6093 | SL-Series | 300SL | 2026-04-04 17:38
| 0 | 700526 | Nucor Towers and Structures | 12004053 | Model IT406 Motorized Pendulum Impact Tester with Digital Display and Enclosure | 1 | 12004053-160 | 2026-10-01 | 366207 | Released |  | 19.4665 | 25.6094 | Met-Impact | IT406 | 2026-04-04 17:38
| 0 | 700524 | Nucor Towers and Structures | 12004053 | Model IT406 Motorized Pendulum Impact Tester with Digital Display and Enclosure | 1 | 12004053-160 | 2026-09-01 | 366203 | Started |  | 19.4666 | 21.3237 | Met-Impact | IT406 | 2026-04-04 17:37
| 0 | 700471 | Element | 09001300 | Model 300SL, Rack & Pinion | 1 | 09001300-CL2-LV | 2026-10-19 | 366129 | Started |  | 19.813 | 28.5273 | SL-Series | 300SL | 2026-04-02 07:25
| 0 | 700241 | Jennmar Corporation | 09002600 | Model 600SL, Rack & Pinion | 1 | 09002600-CL1-HV | 2026-09-14 | 366113 | Released |  | 21.2168 | 24.9311 | SL-Series | 600SL | 2026-03-23 11:34
| 0 | 700233 | Flash Steelworks | 09002610 | Model 600SL, Hydraulic Lever | 1 | 09002610-CL1-HV | 2026-10-29 | 366112 | Released |  | 21.2411 | 31.384 | SL-Series | 600SL | 2026-03-23 07:29
Late | 2.2857 | 599702 | City of Tucson | 03072062 | Retrofit, Super "L" 290/398 Manual (200K-400K) to VMC High Capacity | 1 | 03072062-566789 | 2026-09-14 | 366249 | Released |  | 23.8177 | 27.532 | Retrofit | CNSL-HYD | 2026-03-05 06:37
| 0 | 599466 | Jennmar Corporation of VA, Inc. | 09010600 | Model 2000SL, Rack & Pinion | 1 | 09010600-CL0-HV | 2027-03-08 | 366045 | Released |  | 24.9579 | 53.6721 | SL-Series | 2000SL | 2026-02-25 07:05
| 0 | 599155 | Avient Corporation | 02005261 | Model HDVT3, Heat Deflection | 1 | 02005261-3Station | 2026-09-23 | 365659 | Started |  | 26.7984 | 31.7984 | HDT | HDVT3 | 2026-02-12 09:52
Late | 6.1429 | 598839 | Middle Tennessee State University | 10011130 | Torsion, Model 10,000 in-lb VMC Control, w/ Safety Enclosure | 1 | 10011130-WP110 | 2026-08-25 | 365568 | Started |  | 28.6535 | 29.5106 | Torsion | Torsion | 2026-01-30 10:13
| 0 | 596952 | Tinius Olsen Testing Machine Shanghai Co Ltd | 09002620 | Model 600SL, Compression Only | 1 | 09002620-S-HV | 2026-08-28 | 365450 | Started |  | 30.9428 | 32.2286 | SL-Series | 600SL | 2026-01-14 09:36
| 0 | 596952 | Tinius Olsen Testing Machine Shanghai Co Ltd | 12004051 | Model IT406 Pendulum Impact Tester with Digital Display | 1 | 12004051-220V | 2026-08-28 | 365451 | Started |  | 30.9428 | 32.2286 | Met-Impact | IT406 | 2026-01-14 09:36
| 0 | 596798 | PowerCept Middle East Mechanical & Engineering Equipment Trading LLC | 09010610 | Model 2000SL, Hydraulic Lever | 1 | 09010610-CL0-HV | 2026-10-01 | 365449 | Started |  | 32.85 | 38.9929 | SL-Series | 2000SL | 2026-01-01 01:12
| 0 | 596795 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 12004053 | Model IT406 Motorized Pendulum Impact Tester with Digital Display and Enclosure | 1 | 12004053-260 | 2026-12-14 | 365854 | Released |  | 32.9037 | 49.618 | Met-Impact | IT406 | 2025-12-31 16:10
| 0 | 596795 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 12004053 | Model IT406 Motorized Pendulum Impact Tester with Digital Display and Enclosure | 1 | 12004053-260 | 2026-12-14 | 365855 | Released |  | 32.9037 | 49.618 | Met-Impact | IT406 | 2025-12-31 16:10
| 0 | 596794 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09009410 | Model 1000SL, Hydraulic Lever | 1 | 09009410-CL1-HV | 2026-12-14 | 365908 | Released |  | 32.9037 | 49.618 | SL-Series | 1000SL | 2025-12-31 16:10
| 0 | 596793 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09001310 | Model 300SL, Hydraulic Lever | 1 | 09001310-CL1-HV | 2026-12-14 | 365843 | Released |  | 32.9038 | 49.6181 | SL-Series | 300SL | 2025-12-31 16:10
| 0 | 596793 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09001310 | Model 300SL, Hydraulic Lever | 1 | 09001310-CL1-HV | 2026-12-14 | 365846 | Released |  | 32.9038 | 49.6181 | SL-Series | 300SL | 2025-12-31 16:10
| 0 | 596759 | Pacific Steel Group | 09010630 | Model 2000SL, Sump Pump, Hyd Grips, 1 FT Lgr Adj Columns, Std Screws, High Voltage | 1 | 09010630-596759 | 2026-12-10 | 365365 | Released |  | 33.9261 | 50.069 | SL-Series | 2000SL | 2025-12-24 12:25
| 0 | 596734 | TO Korea Co Ltd | 02005151 | Model HDVT6, Heat Deflection | 1 | 02005151 : 6St | 2026-10-07 | 365312 | Released |  | 34.2256 | 41.2256 | HDT | HDVT6 | 2025-12-22 10:06
| 0 | 596725 | ACUREN | 09009410 | Model 1000SL, Hydraulic Lever | 1 | 09009410-CL2-LV | 2027-02-26 | 365903 | Released |  | 34.7411 | 62.0268 | SL-Series | 1000SL | 2025-12-18 19:30
| 0 | 596655 | KTH Parts Industries Inc. | 09002600 | Model 600SL, Rack & Pinion | 1 | 09002600-CLO-HV | 2026-09-07 | 365267 | Started |  | 35.6108 | 38.3251 | SL-Series | 600SL | 2025-12-12 17:23
| 0 | 596507 | Element | 09001300 | Model 300SL, Rack & Pinion | 1 | 09001300-CL2-LV | 2027-01-26 | 365168 | Released |  | 36.9576 | 59.8147 | SL-Series | 300SL | 2025-12-03 07:07
| 0 | 596498 | ACUREN | 09009410 | Model 1000SL, Hydraulic Lever | 1 | 09009410-CL2-LV | 2026-09-15 | 365341 | Started |  | 37.0568 | 40.9139 | SL-Series | 1000SL | 2025-12-02 14:28
Late | 8.7143 | 596324 | CORINCA CORP IND CENTROAMERICANA | 09010600 | Model 2000SL, Rack & Pinion | 1 | 09010600-CL0-LV | 2026-08-21 | 365072 | Started |  | 39.226 | 39.5118 | SL-Series | 2000SL | 2025-11-17 10:02
Late | 4.1429 | 596256 | GERDAU AMERISTEEL WHITBY | 09010630 | Model 2000SL, Hydraulic Lever, Sump Pump, 2 FT Lgr Adj Columns, Std Screws, HV | 1 | 09010630-596256 | 2026-09-09 | 365274 | Started | Marcus Mihulec | 39.9569 | 42.9569 | SL-Series | 2000SL | 2025-11-12 07:14
| 0 | 595872 | Nucor-Yamato Steel Co. | Fee-999-MetImp | Evaluate for Repair: Metal Impact IT542, SN 319160 | 1 |  | 2026-09-30 | 366649 | Started |  | 44.6349 | 50.6349 | Met-Impact | Misc | 2025-10-10 13:20
Late | 10.7143 | 595518 | Mid-West Mfg. LLC | 09010630 | Model 2000SL Custom to Order, Hyd Lever, Mod Grip Pocket for 3.5" Rounds, Std Fixed Columns, Std Screws, HV | 1 | 09010630-595518 | 2026-08-13 | 364732 | Started |  | 47.7922 | 46.9351 | SL-Series | 2000SL | 2025-09-18 10:54
| 0 | 595132 | Taylor Forge | 09002600 | Model 600SL, Rack & Pinion | 1 | 09002600-CLO-HV | 2026-08-28 | 364461 | Started |  | 51.6577 | 52.9434 | SL-Series | 600SL | 2025-08-22 09:30
| 0 | 594858 | ELLWOOD Materials Technologies Lab Co | 04002600 | Top Level GA, Fit; Automation System; Dual 300SL, Tensile and Hardness; Ellwood | 1 |  | 2026-09-18 | 365434 | Started | Paul Feudo | 54.675 | 58.9607 | Automated | SL-ST | 2025-08-01 06:36
Late | 6.8571 | 593042 | DFAS ROCK ISLAND - HQ0303 | 09001330 | Model 300SL, Custom Hyd, 2 FT Lgr Adj Col, Std Screws, Dust Ignition Proof | 1 | 09001330-593042-699 | 2026-09-23 | 364885 | Started |  | 72.2487 | 77.2487 | SL-Series | 300SL | 2025-03-31 06:13
Late | 6.8571 | 593042 | DFAS ROCK ISLAND - HQ0303 | 09001330 | Model 300SL, Custom Hyd, 2 FT Lgr Adj Col, Std Screws, Dust Ignition Proof | 1 | 09001330-593042-700 | 2026-09-23 | 364886 | Started |  | 72.2487 | 77.2487 | SL-Series | 300SL | 2025-03-31 06:13
Applied filters: ITEMNUMBER is not 02002107 SC2(SalesClassification2) is Electmech, Machine, or Hydraulic SC1 is Automated, FoldingEnd, HDT, Met-Impact, MFI, Plas-Impac, Retrofit, SL-Series, Torsion, or Horizontal Status is not Completed or ReportedFinished SALESORDERPOOLID does not contain 'Consign'